## Product Backlog
s
New Estimate of Effort Remaning as of Sprint
Item | Details (Wiki) | Priority | Status | Initial Estimate | 1 | 2 | 3
As a customer, I want to register my account to use the service |  | High | Done | 4
As a customer, I want to sign in account |  | High | Done | 4
As a customer, I wan to log out account |  | High | Done | 4
As a customer, I want to edit the personal information |  | High | Done | 4
As a customer, I want to select products by category |  | High | Done | 4
As a customer, I want to order a product |  | High | Done | 4
As a customer, I want to search name of product |  | High | Not Started | 4
As a customer, I want to add a product to my cart |  | High | Done | 4
As a customer, I want to add a product to my following |  | High | Done | 3
As a customer, I want to delete a product in my cart |  | High | Done | 4
As a customer, I want to delete a product in my following |  | High | Done | 3
As a customer, I want to see detail of product when I click to image of products |  | High | Done | 4
As a customer, I want to see products sort by category |  | High | Done | 4
As a customer, I want to order a product when click buy now |  | High | Done | 4
As a customer, I want to see my orderdetail when I finish to fill form and click submit |  | High | Done | 4
As a customer, I want to see information about website |  | Nomal | Done | 3
As a customer, I want to see the numbers of item in my cart or in my favorite |  | Normal | Done | 3
As a customer, I want to send contact |  | Nomal | Done | 3
67

## Burndown Chart
Group 1 Burndown Chart
Day
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Hours of Work Remaining Until Completion | 67 | 52.5 | 45.9 | 42.2 | 41.1 | 39.1 | 37.6 | 37.6 | 34.1 | 29.6 | 22.1 | 12.6 | 2.6 | 2.6 | 2.6 | 0.2 | -4.8 | -7.8 | -8.8
| Hours of Work | 14.5 | 6.6 | 3.7 | 1.1 | 2 | 1.5 | 0 | 3.5 | 4.5 | 7.5 | 9.5 | 10 | 0 | 0 | 2.4 | 5 | 3 | 1 | 2 | [10 empty] | 0
| Total hours of work | Day 1: 77.8

## Sprint Backlog #1
SELLING Project Backlog
ID | Task | Responsible | Related Task | Status(Not Started In Progress Completed) | Hours of Work Remaining Until Completion
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Homepage
| Analysis and Design |  | thomlt6 | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | trangnt84 | Done | 0 | 1 | 1 | 0 | 0.5 | 0 | 0
| Write TestCase |  | trangnt84 | Done | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| Acceptance Test |  | trangnt84 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | trangnt84 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Register/Login
| Analysis and Design |  | trangnt83 | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | trangnt83 | Done | 0 | 1 | 2 | 0.5 | 0.5 | 1 | 0
| Write TestCase |  | trangnt83 | Done | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Acceptance Test |  | trangnt83 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | trangnt83 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Display list products
| Analysis and Design |  | TrangPtq5 | Done | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | TrangPtq5 | Done | 0.5 | 1 | 0 | 0 | 0 | 0 | 0
| Write TestCase |  | TrangPtq5 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  | TrangPtq5 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | TrangPtq5 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Display detail product
| Analysis and Design |  | khuyennt7 | Done | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | khuyennt7 | Done | 2 | 1 | 0.5 | 0.5 | 0 | 0 | 0
| Write TestCase |  | hiendt24 | Done | 0 | 0 | 0.1 | 0 | 0 | 0 | 0
| Acceptance Test |  | khuyennt7 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | khuyennt7 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Create order
| Analysis and Design |  | luongNT7 | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | luongNT7 | Done | 3 | 0.5 | 0 | 0 | 0 | 0 | 0
| Write TestCase |  | luongNT7 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  | luongNT7 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | luongNT7 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Create personal page
| Analysis and Design |  | trangnt84 | Done | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | thomlt6 | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Write TestCase |  | hiendt24 | Done | 0 | 0 | 0.1 | 0.1 | 0 | 0 | 0
| Acceptance Test |  | thomlt6 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | thomlt6 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Create your bag/ following
| Analysis and Design |  | trangnt84 | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | hiendt24 | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Write TestCase |  | hiendt24 | Done | 0.5 | 0.1 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  | hiendt24 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  | hiendt24 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | SUM | 14.5 | 6.6 | 3.7 | 1.1 | 2 | 1.5 | 0
|  |  |  | Sum hours | Hours of Work Remaining Until Completion 1: 29.4

## Sprint Backlog #2
SELLING Project Backlog
ID | Task | Responsible | Related Task | Status(Not Started In Progress Completed) | Hours of Work Remaining Until Completion
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Login/ Register/ Log Out
| Analysis and Design |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | hiendt24 | Done | 1.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
| Write TestCase |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Detail Product
| Analysis and Design |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | trangptq5 | Done | 0 | 0 | 1 | 0.5 | 0 | 0 | 0
| Write TestCase |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Profile
| Analysis and Design |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | khuyennt7 | In Progress | 0 | 1 | 2 | 2 | 1 | 0 | 0
| Write TestCase |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | My bag
| Analysis and Design |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | luongnt7 | In Progress | 0 | 1 | 1 | 2 | 2 | 0 | 0
| Write TestCase |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Order
| Analysis and Design |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | trangnt83 | In Progress | 1 | 2 | 2 | 3 | 3 | 0 | 0
| Write TestCase |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | InProgress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ListProduct
| Analysis and Design |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | trangnt84 | In Progress | 0 | 0 | 1 | 0.5 | 2 | 0 | 0
| Write TestCase |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Admin
| Analysis and Design |  | thomlt6 | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0
Code + Unit Test
Write TestCase
Acceptance Test
Writing Materials
8 | Follow
| Analysis and Design |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code + Unit Test |  | thomlt6 | In Progress | 0 | 0.1 | 0.1 | 1 | 2 | 0 | 0
| Write TestCase |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance Test |  |  | In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Writing Materials |  |  | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | SUM | 3.5 | 4.5 | 7.5 | 9.5 | 10 | 0 | 0
|  |  |  | Sum hour | Hours of Work Remaining Until Completion 1: 35

## Sprint Backlog #3
SELLING Project Backlog
ID | Task | Responsible | Related Task | Status(Not Started In Progress Completed) | Hours of Work Remaining Until Completion
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Contact
| Analysis and Design |  | TrangPtq5 | Done | 0 | 1 | 0 | 0 | 0
| Code + Unit Test |  | TrangPtq5 | Done | 0 | 0 | 0 | 0 | 0
Write TestCase
Acceptance Test
Writing Materials
2 | About us
| Analysis and Design |  | trangnt84 | Done | 1 | 1 | 0 | 0 | 0
| Code + Unit Test |  | trangnt84 | Done | 1 | 0 | 0 | 0 | 0
Write TestCase
Acceptance Test
Writing Materials
3 | Add to cart
Analysis and Design
| Code + Unit Test |  | hiendt24 | Done | 0 | 1 | 1 | 0 | 0
| Write TestCase |  | hiendt24 | Done | 0.2 | 0 | 0 | 0 | 0
Acceptance Test
Writing Materials
4 | Add to favorite list
Analysis and Design
| Code + Unit Test |  | hiendt24 | Done | 0 | 0 | 0 | 1 | 1
| Write TestCase |  | hiendt24 | Done | 0.2 | 0 | 0 | 0 | 0
Acceptance Test
Writing Materials
5 | Delete from cart
Analysis and Design
| Code + Unit Test |  | thomlt6 | Done | 0 | 0 | 0 | 1 | 1
| Write TestCase |  | thomlt6 | Done | 0 | 0 | 0 | 0 | 0
Acceptance Test
Writing Materials
6 | Delete from favortie
Analysis and Design
| Code + Unit Test |  | thomlt6 | Done | 0 | 1 | 1 | 0 | 0
| Write TestCase |  | thomlt6 | Done | 0 | 0 | 0 | 0 | 0
Acceptance Test
Writing Materials
7 | Reviews
| Code + Uinit Test |  | hiendt24 | Done | 0 | 0 | 0 | 0 | 1
|  |  |  | SUM | 2.4 | 4 | 2 | 2 | 3
|  |  |  | Sum hours | Hours of Work Remaining Until Completion 1: 13.4